## TASK 1
MAIN GOAL | № | TASKS | STORY POINT | Ideal Hours | Real Hours | PRIORITY
Transport TESLA electric car into the Sun orbit and send it into around Mars orbit as an artificial satellite | 1 | 1. Carry out research: |  |  |  |  | Estimation points summary
| 2 | · Weather conditions | 2 | 2 | 5 | high | 1 | easy breesy
| 3 | calculate the Tesla trajectory in Space | 8 | 170 | 200 | high | 2 | some small task
| 4 | · landind of stages on the floating platform | 8 | 100 | 130 | high | 5 | Medium difficult and important task
| 5 | · Checking car's audio player for playing «Space Oddity» David Bowie | 1 | 1 | 3 | low | 8 | Difficult task
| 6 | · Don’t forgert to clothe the dummy Star Man into Space X space suit | 2 | 1 | 4 | medium | 12 | Very difficult task
| 7 | · Put a copy of Douglas Adams' 1979 novel "The Hitchhiker's Guide to the Galaxy" into the glovebox | 1 | 1 | 3 | low
| 8 | · A towel with an inscription ' don't panic!' | 1 | 1 | 2 | low
| 9 | · Create a cargo place and a new rocket nose to pace a Tesla roadster into | 8 | 80 | 100 | high
| 10 | · Functionality of cameras for shooting "stunning scenery along the road" attached to the car | 2 | 3 | 6 | medium
| 11 | · Tesla as a payload in the test launch of a heavy Falcon Heavy missile | 5 | 20 | 30 | medium
| 12 | 2. permissions:
| 13 | · get a permission from local authorities | 5 | 6 | 12 | high
| 14 | · rent of the launch pad LC-39A from NASA | 5 | 5 | 11 | high
| 15 | · purchase of a quota for pollution of land and atmosphere | 8 | 14 | 30 | high
| 16 | 3. Rocket modernization:
| 17 | · Creation of a 'workhorse' Falcon Heavy | 12 | 600 | 760 | high
| 18 | · Combine the first three steps of Falcon 9 to create a super-rocket | 12 | 760 | 820 | high
| 19 | · Implement a technology that allows the rocket to lift loads up to 60 tons to a low near-Earth orbit and 24 tons to a geostationary | 8 | 380 | 460 | high
| 20 | · The Falcon 9 rocket separation technology | 8 | 400 | 500 | high
| 21 | · Implement a technology that allows Falcon Heavy to become the most powerful modern missile with 27 engines that develop thrust of 2.2 million kg. | 12 | 700 | 830 | high
| 22 | 4. Advertising campaign:
| 23 | · Tesla is the only example of automotive advertising that has been in space and left a mark on history | 5 | 50 | 70 | high
| 24 | · Rocket test | 12 | 590 | 689 | high
| 25 | · Live stream and TV translation of a Falcon launching | 5 | 20 | 35 | high
|  | SUM | 130 | 3904 | 4700
0

## TASK 2
| Planning phase: | This phase will performs only on initial project stages
1 | Tasks analysis | Tasks owerview for whole project
2 | general planning | overall development planning together with development teams and business analysts
3 | Writing test plan | create a test plan document, which will describe in detail the entire testing process, metrics and performance criteria
| Sprint: | All steps will be repeat during every new sprint
1 | planning sprint tasks | planning and estimation of tasks to be taken for the upcoming sprint, role allocation and risk calculation
2 | requirement testing | Testing business documentation, searching for inaccuracies and improving documentation from the perspective of QA
3 | Features testing | verification of functionality that was implemented by developers for non-compliance with requirements
4 | smoke testing | Checking the overall health of the system after integrating new features into it
5 | validation | Checking the fixes of bugs that were opened earlyer to make sure that the opened bugs d no reproduse anymore
6 | retrospective | analysis of the work done for the sprint, reviewing the previously introduced Actions for improving work, making new Actions for the next sprint
| Exploratory testing | Exploratory testing will performs directly before every release
| Exploratory testing | testing of all the new features for unpredictable errors and inconsistencies, checking for the possibility of breaking something in a different way